## Timeline_Plan
PROJECT: Conducting Market Research on Cloud Computing in Vietnam
[Timeline] Timeline Model Base
Date:
SCHEDULE FOR PROCESS AUDITING AND PERFORMANCE REPORTING
ID | Project | Task | Requirement | Challenges, Issues Encountered | Goal | START TIME | END TIME | Extent | Status | Drive/ Github
1 | Document Reading and Information synthesis | - ResearchResearch on the cloud computing market in Vietnam - compile the pricing of Cloud service packages from competitor companies in Vietnam. |  | Don't know how to use R programming to crawler data from a website. | - Price summary table |  |  | - Research | Complete | Báo giá dịch vụ Cloud
[5 empty] | -Data processing & Data visualization of providers' pricing |  |  | - Deep standing | Complete | [Power BI]: https://drive.google.com/file/d/1Q9zvtn6Kce0S5ihOMFnG-L7iTbtri2hV/view?usp=drive_link
[5 empty] | - Building Powerpoint reports |  |  | - Deep standing | Complete | - [Canva]: https://www.canva.com/design/DAGfq0M6Ios/2F9vMIxDMVoMHEehdm_TOA/edit
2 |  | Study detailed information about each product package |  |  | Evaluation table of product packages | 2025-03-01 | 2025-03-04 | - Research | Complete | Báo giá dịch vụ Cloud
3 |  | Researching the needs, challenges, and factors influencing customer's purchase decisions in the Cloud Computing field. |  |  | Customer Segmentation Table with characteristics and main needs of each group. | 2025-03-05 | 2025-03-07 | - Deep standing | Continue to supplement | Chiến lược về giá của Wisdom Cloud
4 |  | Market segmentation by criteria B2B/B2C, business size, and field of operation to understand each customer group. |  |  | Customer Persona Profiles. |  |  | - Deep standing
5 |  | Propose pricing strategies and product packages suitable for each customer segment. |  |  | Table of benefits analysis of each product package by customer group. |  |  | - Deep standing
6 |  | Gather information on competitors' promotional strategies, warranty policies. |  |  | Plan promotional programs for the company's products. |  |  | - Deep standing
|  | IMC Plan |  |  | IMC Plan for Ledhome | 2025-03-13 | 2025-03-14 | - Deep standing | Complete | LEDHOME - IMC PLAN
|  | Create combos from Cloud service packages. |  |  | List of combos | 2025-03-13 | 2025-03-14 | - Deep standing | Complete | Combo package
|  | Propose pricing for service packages. |  |  | The price of the Cloud Server package | 2025-03-17 | 2025-03-18 | - Deep standing | Complete | Báo giá dịch vụ Cloud [Sheet Propose pricing]
|  | Propose pricing for service packages. |  |  | The price of the Cloud Email package | 2025-03-21 | 2025-03-21 |  | Complete | Báo giá dịch vụ Cloud [Sheet Propose pricing]
|  | Propose pricing for service packages. |  |  | The price of the Cloud Security package | 2025-03-22 | 2025-03-22 |  | Complete | Báo giá dịch vụ Cloud [Sheet Propose pricing]
|  | Designing posters for Cloud packages |  |  | posters for Cloud packages | 2025-03-24 | 2025-03-25
|  | Update detailed information for cloud combo packages |  |  | Table of detailed information for cloud combo packages